## Bid Sheet
Opinion of Probable Cost
Cedar River Marina Improvements at Victoria Creek Park |  |  |  | Engineer's Estimate
Pay Item | Description | Unit | Estimated Quantity | Unit Price | Cost | Notes
1 | Mobilization | LS | 1 | 5000 | 5000
2 | Remove, recoat, replace bridge | LS | 1 | 35000 | 35000
3 | Dredge, dispose on site | CY | 2700 | 15 | 40500
4 | Piles | Ea | 90 | 900 | 81000
5 | Decking, framing | SF | 6450 | 15 | 96750
6 | Dry hydrant | Ea | 1 | 5000 | 5000
7 | 4" Concrete | SF | 2300 | 5 | 11500
8 | 8" 22A Aggregate base | SY | 300 | 12 | 3600
9 | Embankment | CY | 50 | 20 | 1000
10 | Canoe/Kayak Launch | Ea | 1 | 10000 | 10000
11 | Tensile Membrane Structures | LS | 1 | 80000 | 80000
12 | Silt fans, accent lighting, electrical | LS | 1 | 10000 | 10000
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
| Total Construction Cost |  |  |  | 379400 | Rounded up to nearest $100
| Design Engineering | Percent | 10% | 38000 | 417400
| Construction Inspection and Testing | Percent | 8% | 30400 | 447800
| Contingency Allowance | Percent | 20% | 89600 | 537400
| Geotechnical Evaluation | LS | 1 | 4000 | 541400
| Permit Fees | LS | 1 | 1000 | 542400
| Total Estimated Project Cost |  |  |  | 542400